## Parivartan- Trucks
Pre-BS VI Trucks Converted
Geography | August |  |  | September (as on 7th) |  |  | Cumulative |  |  | Aggregate
| Actual | Target | %age | Actual | Target | %age | Actual | Target | %age | Actual | Target | %age
Delhi |  | 1276 |  |  | 1914 |  |  | 3190 |  |  | 63795
Haryana |  | 1751 |  |  | 2627 |  |  | 4378 |  |  | 87554
Rajasthan |  | 140 |  |  | 210 |  |  | 350 |  |  | 6997
Uttar Pradesh |  | 658 |  |  | 987 |  |  | 1645 |  |  | 32893
Delhi NCR (Total) |  | 3825 |  |  | 5738 |  |  | 9563 |  |  | 191239
Trucks registered on portal
Geography | Aggregate
| Actual | Target | %age
Delhi |  | 63795
Haryana |  | 87554
Rajasthan |  | 6997
Uttar Pradesh |  | 32893
Delhi NCR (Total) |  | 191239

## Parivartan - Buses
Pre-BS VI Buses Converted
Geography | August |  |  | September (as on 7th) |  |  | Cumulative |  |  | Aggregate
| Actual | Target | %age | Actual | Target | %age | Actual | Target | %age | Actual | Target | %age
Delhi |  | 0 |  |  | 0 |  |  | 0 |  |  | 11
Haryana |  | 212 |  |  | 319 |  |  | 531 |  |  | 10619
Rajasthan |  | 31 |  |  | 46 |  |  | 77 |  |  | 1538
Uttar Pradesh |  | 83 |  |  | 125 |  |  | 208 |  |  | 4161
Delhi NCR (Total) |  | 326 |  |  | 490 |  |  | 816 |  |  | 16329
Buses registered on portal
Geography | Aggregate
| Actual | Target | %age
Delhi |  | 11
Haryana |  | 10619
Rajasthan |  | 1538
Uttar Pradesh |  | 4161
Delhi NCR (Total) |  | 16329

## APCD
APCD installation completed
Geography | Aggregate
| Actual | Target | %age
Delhi | 0 | 48
Haryana | 0 | 1229
Rajasthan | 0 | 244
Uttar Pradesh | 0 | 600
Delhi NCR (Total) | 0 | 2121
Units with applications submitted on portal
Geography |  | August |  |  | September |  |  | Cumulative |  |  | Aggregate
| Till date | Actual | Target | %age | Actual | Target | %age | Actual | Target | %age | Actual | Target | %age
Delhi | 48 |  | 0 |  |  | 24 |  | 48 | 24 | 200% | 48 | 48 | 100%
Haryana | 1229 |  | 0 |  |  | 614 |  | 1229 | 614 | 200.2% | 1229 | 1229 | 100%
Rajasthan | 244 |  | 0 |  |  | 122 |  | 244 | 122 | 200% | 244 | 244 | 100%
Uttar Pradesh | 600 |  | 0 |  |  | 300 |  | 600 | 300 | 200% | 600 | 600 | 100%
Delhi NCR (Total) | 2121 |  | 0 |  |  | 1060 |  | 2121 | 1060 | 200.1% | 2121 | 2121 | 100%

## OCEMS
Industries with no red alerts
Geography | Aggregate
| Actual | Target | %age
Delhi | No data | No data | No data
Haryana | No data | No data | No data
Rajasthan | No data | No data | No data
Uttar Pradesh | No data | No data | No data
Delhi NCR (Total) | No data | No data | No data

## Road Remediation
Road length with end-to-end paving completed
Geography | Till date | August |  |  | September |  |  | Cumulative |  |  | Aggregate
| Actual | Actual | Target | %age | Actual | Target | %age | Actual | Target | %age | Actual | Target | %age
Delhi | 965 |  | 613 |  |  | 613 |  | 965 | 1226 | 78.71% | 965 | 3065 | 31.48%
Uttar Pradesh | 418 |  | 358 |  |  | 358 |  | 418 | 716 | 58.38% | 418 | 1792 | 23.33%
Haryana | 594 |  | 233 |  |  | 233 |  | 594 | 466 | 127.5% | 594 | 1693 | 35.09%
Rajasthan | 61 |  | 50 |  |  | 50 |  | 61 | 100 | 61% | 61 | 307 | 19.87%
Delhi NCR (Total) | 2038 |  | 1254 |  |  | 1254 |  | 2038 | 2508 | 81.26% | 2038 | 6857 | 29.72%

## MRS
Number of MRS deployed for >10m roads
Geography | Till date | Till date |  |  | September |  |  | Cumulative |  |  | Aggregate
| Actual | Actual | Target | %age | Actual | Target | %age | Actual | Target | %age | Actual | Target | %age
Delhi | 98 |  | 2 |  |  | 2 |  | 98 | 102 | 0% | 98 | 171 | 57.31%
Haryana | 75 |  | 6 |  |  | 6 |  | 75 | 75 | 100% | 75 | 105 | 71.43%
Rajasthan | 20 |  | 1 |  |  | 1 |  | 20 | 32 | 62.5% | 20 | 21 | 95.24%
Uttar Pradesh | 45 |  | 0 |  |  | 0 |  | 45 | 47 | 95.74% | 45 | 108 | 41.67%
Delhi NCR (Total) | 238 |  | 9 |  |  | 9 |  | 0 | 256 | 0% | 238 | 405 | 58.77%
Route coverage achieved (%) for >10m roads
Geography | Till date | August |  | September |  | Cumulative |  | Aggregate
| Actual | Actual | Target | Actual | Target | Target | Target | Actual | Target
Delhi |  |  | 55% |  | 56% | No data | 56% | No data | 100%
Haryana |  |  | 65% |  | 71% | No data | 71% | No data | 100%
Rajasthan |  |  | 81% |  | 86% | No data | 86% | No data | 100%
Uttar Pradesh |  |  | 42% |  | 42% | No data | 42% | No data | 100%
Delhi NCR (Total) |  |  |  |  | 58% |  | 58% | 0 | 100%

## SCC
Number of SCCs Operationalised
Geography | Till Date | August |  |  | September |  |  | Cumulative |  |  | Aggregate
| Actual | Actual | Target | %age | Actual | Target | %age | Actual | Target | %age | Actual | Target | %age
Delhi | 0 |  | 0 |  |  | 0 |  | 0 | 0 | NA | 0 | 59 | 0%
Haryana | 24 |  | 12 |  |  | 11 |  | 24 | 47 | 51.06% | 24 | 52 | 46.15%
Rajasthan | 7 |  | 0 |  |  | 0 |  | 7 | 7 | 100% | 7 | 7 | 100%
Uttar Pradesh | 32 |  | 5 |  |  | 5 |  | 32 | 42 | 76.19% | 32 | 37 | 86.49%
Delhi NCR (Total) | 63 |  | 17 |  |  | 16 |  | 63 | 96 | 65.62% | 63 | 155 | 40.65%

## ICCC
Sites compliant with identified interventions
Geography | Aggregate
| Actual | Target | %age
Delhi | 291 | 1869 | 15.57%